## Sheet1
Milestone #1 Switchover from Primary to DR Site
Task ID | Start Date, Time | Finish Date, Time | Finish Date, Time | Organisation | Task Owner | Task Description | Status
1 | 8th Dec, 15:00 CET | 8th Dec, 15:30 CET | 10mins | Infosys | Anish | Send communication to all stake holder for DR Switch
2 | 8th Dec, 15:00 CET | 8th Dec, 15:30 CET | 30mins | Infosys | application | Put all batch jobs on hold for Primary site
3 | 9th Dec, 12:30 CET | 9th Dec, 1:00 CET | 30mins | Infosys | application | Confirmation of completion of all HWA job for business Day end at Primary Site
4 | 9th Dec, 1:00 CET | 9th Dec, 1:30 CET | 30mins | Infosys | DB | Disable OEM alerts for Primary and DR site
5 | 9th Dec, 1:00 CET | 9th Dec, 1:30 CET | 30mins | Infosys | weblogic | Shutdown Application at Primary site
6 | 9th Dec, 1:30 CET | 9th Dec, 1:45 CET | 15mins | Infosys | DB | Stop goldengate services at Primary site
7 | 9th Dec, 1:45 CET | 9th Dec, 2:00 CET | 15mins | Infosys | DB | Check Redo log GAP from Primary site to DR to complete Sync of Data between Primary and DR sitse
8 | 9th Dec, 2:00 CET | 9th Dec, 3:30 CET | 1.5hr | Infosys | DB | Switch Role from Primary site to DR site by Dataguard borker Vice versa.
9 | 9th Dec, 3:30 CET | 9th Dec, 3:45 CET | 15mins | Infosys | DB | Check on DR site both dataabase INSISDR and REPOSDB open for Read write mode
10 | 9th Dec, 3:45 CET | 9th Dec, 4:00 CET | 15mins | Infosys | DB | Check at Primary site database INSISDB and REPOSDR in recovery mode
11 | 9th Dec, 4:00 CET | 9th Dec, 4:30 CET | 30mins | Infosys | DB | Check Data replication is happening from DR site to Primary site
12 | 9th Dec, 4:30 CET | 9th Dec, 4:40 CET | 10mins | Infosys | DB | Share DB details with Weblogic team
13 | 9th Dec, 5:00 CET | 9th Dec, 12:00 CET | 7hrs | Infosys | weblogic | Weblogic and BI Env provisioning
|  | 9th Dec, 10:00 CET | 5hrs
14 | 9th Dec, 12:00 CET | 9th Dec, 12:15 CET | 15mins | Infosys | DB | Enable the DR SYNC between primary & standby
| 9th Dec, 10:00 CET | 9th Dec, 10:15 CET
15 | 9th Dec, 12:15 CET | 9th Dec, 12:30 CET | 15mins | Infosys | DB | create restore point on the primary site
| 9th Dec, 10:15 CET | 9th Dec, 10:30 CET
16 | 9th Dec, 13:00 CET | 9th Dec, 15:00 CET | 2hrs | Infosys | weblogic | Deployment of Latest artifacts and Shared Libraries
| 9th Dec, 10:30 CET | 9th Dec, 12:30 CET
17 | 9th Dec, 13:00 CET | 9th Dec, 15:00 CET | 2hrs | Infosys | weblogic | Deploy data model and reports from Production
| 9th Dec, 10:30 CET | 9th Dec, 12:30 CET
18 | 9th Dec, 14:00 CET | 9th Dec, 14:15 CET | 15mins | GEMI Team | GEMI Team | Adding DR server details in PING Agent - Production
| 9th Dec, 11:45 CET | 9th Dec, 12:00 CET
19 | 9th Dec, 14:00 CET | 9th Dec, 14:15 CET | 15mins | LF DNS Team | DNS team | Remaping of DNS from primary site load balancer to DR site
| 9th Dec, 11:45 CET | 9th Dec, 12:00 CET
20 | 9th Dec, 15:00 CET | 9th Dec, 15:30 CET | 30mins | Infosys | DB & weblogic | Sanity checks
| 9th Dec, 12:30 CET | 9th Dec, 13:00 CET
21 | 9th Dec, 14:00 CET | 9th Dec, 14:30 CET | 30 mins | Infosys | application | Create new variable table and job stream for DR to test the connectivity by scheduling Close_DM and test jobs
| 9th Dec, 13:00 CET | 9th Dec, 13:30 CET
22 | 9th Dec, 16:00 CET | 9th Dec, 18:00 CET | 2 hr | LF | SMRs | Business verification
| 9th Dec, 13:30 CET | 9th Dec, 15:30 CET
23 | 9th Dec, 15:00 CET | 9th Dec, 20:00 CET | 5 hrs | TCS | Unix,Windows,Firewall, Network and Storage | Standby support
|  |  |  | Integrations | DSL, EPA, DSLSAK, VL, Skavi, GEMI
24 | 9th Dec, 18:00 CET | 9th Dec, 18:30 CET | 30 mins | LF | Business | Go No-Go Decison
| 9th Dec, 15:30 CET | 9th Dec, 15:40 CET | 10 mins
25 | 9th Dec, 18:30 CET | 9th Dec, 18:45 CET | 15 mins | Infosys | application | Validation of HWA jobs (Test jobs)
| 9th Dec, 15:40 CET | 9th Dec, 15:45 CET | 5 mins
Milestone #2 Switchover from DR to Primary Site
26 | 9th Dec, 19:00 CET | 9th Dec, 19:15 CET | 15 mins | Infosys | weblogic | Shutdown Application and BI at DR site
| 9th Dec, 15:45 CET | 9th Dec, 16:00 CET
27 | 9th Dec, 19:00 CET | 9th Dec, 19:15 CET | 15 mins | LF DNS Team | DNS team | Remaping of DNS to primary site load balancer
| 9th Dec, 16:00 CET | 9th Dec, 16:15 CET
28 | 9th Dec, 19:15 CET | 9th Dec, 19:30 CET | 15mins | Infosys | DB | Check at Primary site database INSISDB and REPOSDR in recovery mode
| 9th Dec, 16:15 CET | 9th Dec, 17:00 CET | 45mins
29 | 9th Dec, 19:30 CET | 9th Dec, 19:45 CET | 15mins | Infosys | DB | Check Redo log GAP from DR to Primary Site to complete Sync of Data betweenDR and Primary site
| 9th Dec, 16:15 CET | 9th Dec, 17:00 CET | 45mins
30 | 9th Dec, 19:45 CET | 9th Dec, 21:15 CET | 1.5hr | Infosys | DB | Switch Role from DR site o Primary site by Dataguard borker Vice versa.
| 9th Dec, 16:15 CET | 9th Dec, 17:00 CET | 45mins
31 | 9th Dec, 21:15 CET | 9th Dec, 21:30 CET | 15mins | Infosys | DB | Check on Primary site both dataabase INSISDB and REPOSDR open for Read write mode
| 9th Dec, 16:15 CET | 9th Dec, 17:00 CET | 45mins
32 | 9th Dec, 21:30 CET | 9th Dec, 22:00 CET | 30mins | Infosys | DB | Check Data replication is happening from Primary site to DR Site
| 9th Dec, 16:15 CET | 9th Dec, 17:00 CET | 45mins
33 | 9th Dec, 22:00 CET | 9th Dec, 22:15 CET | 15mins | Infosys | DB | Start Golden gate extraction/replication service
| 9th Dec, 17:00 CET | 9th Dec, 17:15 CET
34 | 9th Dec, 22:15 CET | 9th Dec, 22:45 CET | 30mins | Infosys | weblogic | Start application on Primary site
| 9th Dec, 17:15 CET | 9th Dec, 17:30 CET | 15mins
35 | 9th Dec, 22:30 CET | 9th Dec, 23:30 CET | 1 hr | LF | SMRs | Business verification
| 9th Dec, 17:30 CET | 9th Dec, 18:00 CET | 30mins
36 | 9th Dec, 23:30 CET | 10th Dec, 00:00 CET | 30 mins | Infosys | DB | Enable OEM jobs and alerts
| 9th Dec, 18:00 CET | 9th Dec, 18:15 CET | 15 mins
37 | 9th Dec, 23:30 CET |  |  | Infosys | Application | Enable HWA jobs at Primary site
9th Dec, 18:15 CET