## Runbook
High Level Steps
Task ID | Task Description | Start Date, Time | Finish Date, Time | Time Taken | Task Owner | Status | Performed By | Remarks
1 | Place DB restoration request with TCS | 16-06-2025 12.15 CET | 16-06-2025 12.20 CET | 5 mins | DBA | Completed
2 | Prepare database for restoration |  |  | 55 mins | DBA | #NAME? |  | 15 minutes of the activity were completed the previous day, and 40 minutes were done on the day of the activity. | Check if there are any environment is available - Kedar
3 | Initiate database restoration from COMMVAULT | 17-06-2025 09.20 CET | 17-06-2025 11.50 CET | 2 hr 30 mins | DBA/TCS | Completed
4 | Post-Restoration Validation | 17-06-2025 12.00 CET | 17-06-2025 12.45 CET | 45 mins | DBA | Completed |  | This activity can be performed in parallel with the WebLogic build. However, since the WebLogic resource was occupied with production work, the build started late. Therefore, 30 minutes can be excluded from the RTO calculation.
5 | Build Weblogic domain | 17-06-2025 13.55 CET | 17-06-2025 15.06 CET | 63 mins | WLA | Completed
6 | Deploy latest artifacts |  |  | 37 mins | WLA | Completed |  | After this phase, EttSAK application will be up and running.
7 | Smoke test |  |  |  | WLA/APP | Completed

## Detailed steps
Database prerequisites
Task | Description | Remarks | Start date, time | End date, time | Task Owner | Time Taken (mins)
1 | Check if we can restore data from PROD TO BLITZER | Completed | 16-06-2025(11.00 CET) | 16-06-2025(11.20 CET) | DBA (Kedar) | 10
2 | Check Available Disk Space in BLITZER server | Passed (we have enough space) Required : 9800GB Available : 11264GB | 16-06-2025(11.30 CET) | 16-06-2025(11.35 CET) | DBA (Kedar) | 5
3 | Create Parameter file(pfile) based on Prod | Completed - We have created the pfile | 17-06-2025(7.00 CET) | 17-06-2025(7.05 CET) | DBA (Kedar) | 10
4 | Database should be running with spfile(to avoid issues) | Completed - DB is running with SPFILE | 17-06-2025(7.05 CET) | 17-06-2025(7.10 CET) | DBA (Kedar) | 5
5 | Undotbs parameter should be set same as source(Prod) database. | Completed - We have created the UNDO tablespace | 17-06-2025(7.15 CET) | 17-06-2025(7.20 CET) | DBA (Kedar) | 5
6 | Add the ENCRYPTION_WALLET_LOCATION parameter to both database Oracle Home sqlnet.ora file and Grid Home sqlnet.ora file. | Completed- Copied the wallet files from source to destination | 17-06-2025(7.20 CET) | 17-06-2025(7.25 CET) | DBA (Kedar) | 5
7 | Copy the TDE wallet files to the server | Completed-- Copied the files from source to destination | 17-06-2025(7.25 CET) | 17-06-2025(7.30 CET) | DBA (Kedar) | 5
8 | Source and target database should be of same version | Completed-- Checked the DB versions
9 | Set db_recovery_file_dest_size to 200G | Completed-- Parameter set to 200GB | 17-06-2025(7.30 CET) | 17-06-2025(7.35 CET) | DBA (Kedar) | 5
10 | Check for temp tablespace, it should have atleast 1 datafile | Completed-- Added one temp datafile | 17-06-2025(7.35 CET) | 17-06-2025(7.40 CET) | DBA (Kedar) | 5
55
Post database restoration
Task | Description | Remarks | Start date, time | End date, time | Task Owner | Time Taken (mins)
1 | DBID should be changed after restore | Completed-- DB id was changed successfully | 17-06-2025(12.00 CET) | 17-06-2025(12.10 CET) | DBA (Kedar) | 10
2 | Check for local_listener | Completed- Listeners are up and running fine | 17-06-2025(12.10 CET) | 17-06-2025(12.15 CET) | DBA (Kedar) | 5
3 | Check connectivity to database | Completed- Connectivity looks good | 17-06-2025(12.15 CET) | 17-06-2025(12.25 CET) | DBA (Kedar) | 10
4 | Verify that it is production data | Completed- Data is same as production | 17-06-2025(12.25 CET) | 17-06-2025(12.30 CET) | DBA (Kedar) | 5
5 | Change sys and schema password after restore | Completed | 17-06-2025(12.30 CET) | 17-06-2025(12.35 CET) | DBA (Kedar) | 5
6 | Update liquibase users password | Completed | 17-06-2025(12.35 CET) | 17-06-2025(12.40 CET) | DBA (Kedar) | 5
7 | Update operartion date | Completed | 17-06-2025(12.40 CET) | 17-06-2025(12.45 CET) | DBA (Kedar) | 5
8 | Update policy and claim sequences.
45
Build Weblogic domain
Task | Description | Remarks | Start date, time | End date, time | Task Owner | Time Taken (mins)
1 | Cleanup existing domin |  | 17-06-2025 13.55 CET | 17-06-2025 13.58 CET | WLA (Priyanka) | 3
2 | Update property(yml) files if needed | This step is not needed, as there is no change |  |  | WLA (Priyanka)
3 | Run below roles: java,weblogic_infrastructure,weblogic_deploy_tooling,opatch,weblogic_patches,apache,create_domain,create_managed_domain_template,create_managed_domain,shared_folder_move_link_managed |  | 17-06-2025 13.58 CET | 17-06-2025 14.30 CET | WLA (Priyanka) | 32
4 | start_admin_nodemanager,start_managed_nodemanager,start_admin |  | 17-06-2025 14.35 CET | 17-06-2025 14.45 CET | WLA (Priyanka) | 10
5 | predeployment,setup_ovd_config,provider |  | 17-06-2025 14.45 CET | 17-06-2025 14.48 CET | WLA (Priyanka) | 3
6 | create_update_deployment_config |  | 17-06-2025 15.00 CET | 17-06-2025 15.02 CET | WLA (Priyanka) | 2
7 | provisison_database_users, configure_domain |  | 17-06-2025 15.05 CET | 17-06-2025 15.06 CET | WLA (Priyanka) | 1
8 | Create MDS File structure |  |  |  | WLA (Priyanka)
9 | Create codebase policy |  | 17-06-2025 14.48 CET | 17-06-2025 15.00 CET | WLA (Priyanka) | 12
63
Deploy latest artifacts
Task | Description | Remarks | Start date, time | End date, time | Task Owner | Time Taken (mins)
1 | Shared Lib |  | 17-06-2025 15.06 CET | 17-06-2025 15.20 CET | WLA (Priyanka) | 14
2 | CustDB, Dirty prodhopp, FileAdaptor, Insure Overview, Integration Interfaces, Quickclaim, Integration Gateway, Internal API |  | 17-06-2025 15.20 CET | 17-06-2025 15.30 CET | WLA (Priyanka) | 10
3 | InsisLfue, InsisMds |  | 18-06-2025 15.32 CET | 18-06-2025 15.45 CET | WLA (Priyanka) | 13
37
Smoke test
Task | Description | Remarks | Start date, time | End date, time | Task Owner | Time Taken (mins)
1 | Create Household policy |  | 2025-06-19, 12:54:00 | 2025-06-19, 12:57:00 | App (Anupriya)
2 | Create Accident policy |  | 2025-06-19, 13:08:00 | 2025-06-19, 13:12:00 | App (Anupriya)
3 | Create claim for the policy |  | 2025-06-19, 13:02:00 | 2025-06-19, 13:04:00 | App (Anupriya)
4 | Check local print |  | 2025-06-19, 13:14:00 | 2025-06-19, 13:18:00 | App (Anupriya)

## DB details
Source server | Source database | Target serer | Target database
insis-db-scan.lfnet.se | ESAKDB (RAC) | E75LRL1545v.lfnet.se (Sollentuna) | BLITZER (Single instance)